## Sheet1
Final Steps - WIP Items | Status | Status after discussion | Status as on 1st July | Timelines
Free courses --- Add one more menu for free courses in the student login. All the free courses(fee is 0) will appear in the page .on click of course box subscription should happen (without payment flow) and should display in the same page under "My free courses" title | In Phase 1 - Agreed | Will be done | Completed
Payment gateway - we need to integrate with foreign currency | In Phase 1 – Agreed | Will be done when the payment details is available. Only USD and INR will be supported
Website integration - Need to get inputs from Visu (Ask analytics) (AA will be providing this) | In Phase 1 - Agreed | Will be done once the website is available
Course Icon size - Will be provide by Visu and Nirmal (AA will be providing this) | In Phase 1 - Agreed | Will be done when the icons are ready
Analytics report (Google) (AA will be providing this) | In Phase 1 – Agreed | Will be done once the code is available.
Quiz – captiva content will be displayed. | In Phase 1 - Agreed |  | Not yet received Captiva Quiz file.
SPOC's license default count will be "0". | In Phase 1 - Agreed |  | Completed
Admin can delete the AOI request record which status is "Work in Progress". Should be reflect in the SPOC login and Available AOI. | In Phase 1 - Agreed |  | Completed
SPOC - Myuser page should have parent/child UI. Affiliate and SME - Myuser page will have UI in tabular form. | In Phase 1 - Agreed |  | Completed
When we download mentor/SME resources, file name should be prefix with respective SME reg.No. | In Phase 1 - Agreed |  | Completed
Organization SPOC - term change as SPOC's. | In Phase 1 - Agreed |  | Completed
When we create Mentor/SME need to add "Course" in super admin login. Need to show the student subscription count in mentor/SME login. | In Phase 1 - Agreed |  | Completed
the User can buy the same course again (Not sure of the status) | In Phase 1 – Agreed |  | Completed
Users can make as many attempts as they want till they reach the pass score. The answers must be visible to them only after they pass the test. The weightage given to each question is 1. Ranks to be compared by country, area of interest. Each Area of Interest needs to have a separate ranking per user (Request a discussion) | 2BDiscussed | Area of interest is still debated. Rest can be done on phase 1.
User Attributes: Other Countries need to be added (Not sure of the status) | In Phase 1 – Agreed |  | Completed
Users can make as many attempts as they want till they reach the pass score (of 80%) . The answers must be visible to them only after they pass the test | In Phase 1 – Agreed |  | Completed
Mentor/SME can see his/her resources and that recourses mapped with course which are published. no.of users subscribed the courses. | In Phase 1 – Agreed |  | Completed
Link and unlink the courses with Mentor/SME | In Phase 1 – Agreed |  | Completed
Hierachy UI changes in User login |  |  | Work in progress | 2015-07-01